## Raw_data
Project_ID | Project_Name | Category | Item_Description | Budgeted_Cost_NGN | Actual_Cost_NGN | Month | Project_Phase
PRJ-001 | Lekki Primary School Block A | Materials | Cement and concrete works | 2500000 | 2870000 | 2024-01-01 | Foundation
PRJ-001 | Lekki Primary School Block A | Labour | Concrete gang - foundation | 1800000 | 1950000 | 2024-01-01 | Foundation
PRJ-001 | Lekki Primary School Block A | Equipment | Concrete mixer hire | 450000 | 450000 | 2024-01-01 | Foundation
PRJ-002 | Surulere Health Centre Renovation | Materials | Roofing sheets and trusses | 3200000 | 3100000 | 2024-02-01 | Superstructure
PRJ-002 | Surulere Health Centre Renovation | Labour | Carpentry and roofing | 2100000 | 2350000 | 2024-02-01 | Superstructure
PRJ-002 | Surulere Health Centre Renovation | Equipment | Scaffolding hire | 600000 | 600000 | 2024-02-01 | Superstructure
PRJ-003 | Ikeja Road Drainage Rehabilitation | Materials | Precast drain channels | 5500000 | 6200000 | 2024-02-01 | Foundation
PRJ-003 | Ikeja Road Drainage Rehabilitation | Labour | Excavation and laying | 3800000 | 4100000 | 2024-03-01 | Foundation
PRJ-003 | Ikeja Road Drainage Rehabilitation | Equipment | Excavator hire | 1200000 | 1350000 | 2024-03-01 | Foundation
PRJ-004 | Yaba Community Hall Extension | Materials | Blocks and mortar | 1900000 | 1850000 | 2024-03-01 | Superstructure
PRJ-004 | Yaba Community Hall Extension | Labour | Block laying gang | 1400000 | 1400000 | 2024-03-01 | Superstructure
PRJ-004 | Yaba Community Hall Extension | Materials | Steel reinforcement | 2200000 | 2480000 | 2024-04-01 | Superstructure
PRJ-005 | Apapa Staff Quarters Block B | Materials | Electrical fittings and wiring | 1600000 | 1590000 | 2024-04-01 | Finishing
PRJ-005 | Apapa Staff Quarters Block B | Labour | Electrical installation | 1100000 | 1250000 | 2024-04-01 | Finishing
PRJ-005 | Apapa Staff Quarters Block B | Materials | Plumbing pipes and fittings | 980000 | 1040000 | 2024-04-01 | Finishing
PRJ-006 | Mushin Market Redevelopment | Materials | Cement and concrete works | 4800000 | 5100000 | 2024-05-01 | Foundation
PRJ-006 | Mushin Market Redevelopment | Labour | Concrete gang - slabs | 3200000 | 3200000 | 2024-05-01 | Foundation
PRJ-006 | Mushin Market Redevelopment | Equipment | Tower crane hire | 2500000 | 2750000 | 2024-05-01 | Superstructure
PRJ-007 | Gbagada Secondary School Library | Materials | Roofing and ceiling | 2700000 | 2650000 | 2024-05-01 | Finishing
PRJ-007 | Gbagada Secondary School Library | Labour | Finishing and painting | 1500000 | 1680000 | 2024-06-01 | Finishing
PRJ-007 | Gbagada Secondary School Library | Materials | Doors and windows | 1800000 | 1920000 | 2024-06-01 | Finishing
PRJ-008 | Ojota Pedestrian Bridge | Materials | Steel fabrication | 8500000 | 9200000 | 2024-06-01 | Superstructure
PRJ-008 | Ojota Pedestrian Bridge | Labour | Steel erection | 4200000 | 4500000 | 2024-07-01 | Superstructure
PRJ-008 | Ojota Pedestrian Bridge | Equipment | Mobile crane hire | 1800000 | 1800000 | 2024-07-01 | Superstructure
PRJ-009 | Badagry Waterfront Promenade | Materials | Interlocking paving | 3600000 | 3450000 | 2024-07-01 | Finishing
PRJ-009 | Badagry Waterfront Promenade | Labour | Paving gang | 2000000 | 2050000 | 2024-07-01 | Finishing
PRJ-009 | Badagry Waterfront Promenade | Materials | Lighting fixtures | 1200000 | 1350000 | 2024-08-01 | Finishing
PRJ-010 | Ikorodu Bus Terminal Phase 2 | Materials | Concrete pavement | 6200000 | 6800000 | 2024-08-01 | Foundation
PRJ-010 | Ikorodu Bus Terminal Phase 2 | Labour | Earthworks and compaction | 3500000 | 3700000 | 2024-08-01 | Foundation
PRJ-010 | Ikorodu Bus Terminal Phase 2 | Equipment | Compactor and grader hire | 1500000 | 1500000 | 2024-09-01 | Foundation
PRJ-011 | Victoria Island Office Complex | Materials | Curtain wall glazing | 12000000 | 13500000 | 2024-09-01 | Finishing
PRJ-011 | Victoria Island Office Complex | Labour | Glazing installation | 4500000 | 4800000 | 2024-09-01 | Finishing
PRJ-011 | Victoria Island Office Complex | Materials | Floor tiling - marble | 5800000 | 5650000 | 2024-10-01 | Finishing
PRJ-012 | Agege Primary School Classrooms | Materials | Blocks and mortar | 1700000 | 1700000 | 2024-10-01 | Superstructure
PRJ-012 | Agege Primary School Classrooms | Labour | Block laying and plastering | 1300000 | 1420000 | 2024-10-01 | Superstructure
PRJ-012 | Agege Primary School Classrooms | Materials | Roofing sheets | 1400000 | 1380000 | 2024-11-01 | Superstructure
PRJ-013 | Epe Resort Access Road | Materials | Asphalt and base course | 9500000 | 10200000 | 2024-11-01 | Superstructure
PRJ-013 | Epe Resort Access Road | Labour | Asphalt laying gang | 4800000 | 5100000 | 2024-11-01 | Superstructure
PRJ-013 | Epe Resort Access Road | Equipment | Asphalt paver hire | 2200000 | 2200000 | 2024-12-01 | Superstructure
PRJ-014 | Ajah Affordable Housing Block C | Materials | Concrete frame works | 7200000 | 7050000 | 2024-11-01 | Superstructure
PRJ-014 | Ajah Affordable Housing Block C | Labour | Formwork and concrete | 4100000 | 4350000 | 2024-12-01 | Superstructure
PRJ-014 | Ajah Affordable Housing Block C | Materials | Electrical and mechanical | 3300000 | 3480000 | 2024-12-01 | Finishing
PRJ-015 | Oshodi Transport Interchange | Materials | Structural steel | 11000000 | 11800000 | 2024-12-01 | Superstructure
PRJ-015 | Oshodi Transport Interchange | Labour | Structural steel erection | 5500000 | 5900000 | 2024-12-01 | Superstructure
PRJ-015 | Oshodi Transport Interchange | Equipment | Heavy crane and rigging | 3000000 | 3000000 | 2024-12-01 | Superstructure
PRJ-016 | Shomolu Staff Clinic | Materials | Block work and plaster | 1600000 | 1550000 | 2024-01-01 | Superstructure
PRJ-016 | Shomolu Staff Clinic | Labour | Masonry gang | 1100000 | 1180000 | 2024-02-01 | Superstructure
PRJ-016 | Shomolu Staff Clinic | Materials | Roofing and ceiling | 1350000 | 1420000 | 2024-03-01 | Finishing
PRJ-017 | Alimosho Model School | Materials | Ceramic floor tiles | 2100000 | 2080000 | 2024-04-01 | Finishing
PRJ-017 | Alimosho Model School | Labour | Tiling and screeding | 1400000 | 1500000 | 2024-05-01 | Finishing
PRJ-017 | Alimosho Model School | Materials | Painting and surface prep | 900000 | 970000 | 2024-06-01 | Finishing

## Cleaned_data
Project_ID | Project_Name | Category | Item_Description | Budgeted_Cost_NGN | Actual_Cost_NGN | Month | Project_Phase | Variance_NGN | Variance_Pct | Budget_status
PRJ-001 | Lekki Primary School Block A | Materials | Cement and concrete works | 2500000 | 2870000 | 2024-01-01 | Foundation | 370000 | 14.8 | Over Budget
PRJ-001 | Lekki Primary School Block A | Labour | Concrete gang - foundation | 1800000 | 1950000 | 2024-01-01 | Foundation | 150000 | 8.3333 | Over Budget
PRJ-001 | Lekki Primary School Block A | Equipment | Concrete mixer hire | 450000 | 450000 | 2024-01-01 | Foundation | 0 | 0 | Under Budget
PRJ-002 | Surulere Health Centre Renovation | Materials | Roofing sheets and trusses | 3200000 | 3100000 | 2024-02-01 | Superstructure | -100000 | -3.125 | Under Budget
PRJ-002 | Surulere Health Centre Renovation | Labour | Carpentry and roofing | 2100000 | 2350000 | 2024-02-01 | Superstructure | 250000 | 11.9048 | Over Budget
PRJ-002 | Surulere Health Centre Renovation | Equipment | Scaffolding hire | 600000 | 600000 | 2024-02-01 | Superstructure | 0 | 0 | Under Budget
PRJ-003 | Ikeja Road Drainage Rehabilitation | Materials | Precast drain channels | 5500000 | 6200000 | 2024-02-01 | Foundation | 700000 | 12.7273 | Over Budget
PRJ-003 | Ikeja Road Drainage Rehabilitation | Labour | Excavation and laying | 3800000 | 4100000 | 2024-03-01 | Foundation | 300000 | 7.8947 | Over Budget
PRJ-003 | Ikeja Road Drainage Rehabilitation | Equipment | Excavator hire | 1200000 | 1350000 | 2024-03-01 | Foundation | 150000 | 12.5 | Over Budget
PRJ-004 | Yaba Community Hall Extension | Materials | Blocks and mortar | 1900000 | 1850000 | 2024-03-01 | Superstructure | -50000 | -2.6316 | Under Budget
PRJ-004 | Yaba Community Hall Extension | Labour | Block laying gang | 1400000 | 1400000 | 2024-03-01 | Superstructure | 0 | 0 | Under Budget
PRJ-004 | Yaba Community Hall Extension | Materials | Steel reinforcement | 2200000 | 2480000 | 2024-04-01 | Superstructure | 280000 | 12.7273 | Over Budget
PRJ-005 | Apapa Staff Quarters Block B | Materials | Electrical fittings and wiring | 1600000 | 1590000 | 2024-04-01 | Finishing | -10000 | -0.625 | Under Budget
PRJ-005 | Apapa Staff Quarters Block B | Labour | Electrical installation | 1100000 | 1250000 | 2024-04-01 | Finishing | 150000 | 13.6364 | Over Budget
PRJ-005 | Apapa Staff Quarters Block B | Materials | Plumbing pipes and fittings | 980000 | 1040000 | 2024-04-01 | Finishing | 60000 | 6.1224 | Over Budget
PRJ-006 | Mushin Market Redevelopment | Materials | Cement and concrete works | 4800000 | 5100000 | 2024-05-01 | Foundation | 300000 | 6.25 | Over Budget
PRJ-006 | Mushin Market Redevelopment | Labour | Concrete gang - slabs | 3200000 | 3200000 | 2024-05-01 | Foundation | 0 | 0 | Under Budget
PRJ-006 | Mushin Market Redevelopment | Equipment | Tower crane hire | 2500000 | 2750000 | 2024-05-01 | Superstructure | 250000 | 10 | Over Budget
PRJ-007 | Gbagada Secondary School Library | Materials | Roofing and ceiling | 2700000 | 2650000 | 2024-05-01 | Finishing | -50000 | -1.8519 | Under Budget
PRJ-007 | Gbagada Secondary School Library | Labour | Finishing and painting | 1500000 | 1680000 | 2024-06-01 | Finishing | 180000 | 12 | Over Budget
PRJ-007 | Gbagada Secondary School Library | Materials | Doors and windows | 1800000 | 1920000 | 2024-06-01 | Finishing | 120000 | 6.6667 | Over Budget
PRJ-008 | Ojota Pedestrian Bridge | Materials | Steel fabrication | 8500000 | 9200000 | 2024-06-01 | Superstructure | 700000 | 8.2353 | Over Budget
PRJ-008 | Ojota Pedestrian Bridge | Labour | Steel erection | 4200000 | 4500000 | 2024-07-01 | Superstructure | 300000 | 7.1429 | Over Budget
PRJ-008 | Ojota Pedestrian Bridge | Equipment | Mobile crane hire | 1800000 | 1800000 | 2024-07-01 | Superstructure | 0 | 0 | Under Budget
PRJ-009 | Badagry Waterfront Promenade | Materials | Interlocking paving | 3600000 | 3450000 | 2024-07-01 | Finishing | -150000 | -4.1667 | Under Budget
PRJ-009 | Badagry Waterfront Promenade | Labour | Paving gang | 2000000 | 2050000 | 2024-07-01 | Finishing | 50000 | 2.5 | Over Budget
PRJ-009 | Badagry Waterfront Promenade | Materials | Lighting fixtures | 1200000 | 1350000 | 2024-08-01 | Finishing | 150000 | 12.5 | Over Budget
PRJ-010 | Ikorodu Bus Terminal Phase 2 | Materials | Concrete pavement | 6200000 | 6800000 | 2024-08-01 | Foundation | 600000 | 9.6774 | Over Budget
PRJ-010 | Ikorodu Bus Terminal Phase 2 | Labour | Earthworks and compaction | 3500000 | 3700000 | 2024-08-01 | Foundation | 200000 | 5.7143 | Over Budget
PRJ-010 | Ikorodu Bus Terminal Phase 2 | Equipment | Compactor and grader hire | 1500000 | 1500000 | 2024-09-01 | Foundation | 0 | 0 | Under Budget
PRJ-011 | Victoria Island Office Complex | Materials | Curtain wall glazing | 12000000 | 13500000 | 2024-09-01 | Finishing | 1500000 | 12.5 | Over Budget
PRJ-011 | Victoria Island Office Complex | Labour | Glazing installation | 4500000 | 4800000 | 2024-09-01 | Finishing | 300000 | 6.6667 | Over Budget
PRJ-011 | Victoria Island Office Complex | Materials | Floor tiling - marble | 5800000 | 5650000 | 2024-10-01 | Finishing | -150000 | -2.5862 | Under Budget
PRJ-012 | Agege Primary School Classrooms | Materials | Blocks and mortar | 1700000 | 1700000 | 2024-10-01 | Superstructure | 0 | 0 | Under Budget
PRJ-012 | Agege Primary School Classrooms | Labour | Block laying and plastering | 1300000 | 1420000 | 2024-10-01 | Superstructure | 120000 | 9.2308 | Over Budget
PRJ-012 | Agege Primary School Classrooms | Materials | Roofing sheets | 1400000 | 1380000 | 2024-11-01 | Superstructure | -20000 | -1.4286 | Under Budget
PRJ-013 | Epe Resort Access Road | Materials | Asphalt and base course | 9500000 | 10200000 | 2024-11-01 | Superstructure | 700000 | 7.3684 | Over Budget
PRJ-013 | Epe Resort Access Road | Labour | Asphalt laying gang | 4800000 | 5100000 | 2024-11-01 | Superstructure | 300000 | 6.25 | Over Budget
PRJ-013 | Epe Resort Access Road | Equipment | Asphalt paver hire | 2200000 | 2200000 | 2024-12-01 | Superstructure | 0 | 0 | Under Budget
PRJ-014 | Ajah Affordable Housing Block C | Materials | Concrete frame works | 7200000 | 7050000 | 2024-11-01 | Superstructure | -150000 | -2.0833 | Under Budget
PRJ-014 | Ajah Affordable Housing Block C | Labour | Formwork and concrete | 4100000 | 4350000 | 2024-12-01 | Superstructure | 250000 | 6.0976 | Over Budget
PRJ-014 | Ajah Affordable Housing Block C | Materials | Electrical and mechanical | 3300000 | 3480000 | 2024-12-01 | Finishing | 180000 | 5.4545 | Over Budget
PRJ-015 | Oshodi Transport Interchange | Materials | Structural steel | 11000000 | 11800000 | 2024-12-01 | Superstructure | 800000 | 7.2727 | Over Budget
PRJ-015 | Oshodi Transport Interchange | Labour | Structural steel erection | 5500000 | 5900000 | 2024-12-01 | Superstructure | 400000 | 7.2727 | Over Budget
PRJ-015 | Oshodi Transport Interchange | Equipment | Heavy crane and rigging | 3000000 | 3000000 | 2024-12-01 | Superstructure | 0 | 0 | Under Budget
PRJ-016 | Shomolu Staff Clinic | Materials | Block work and plaster | 1600000 | 1550000 | 2024-01-01 | Superstructure | -50000 | -3.125 | Under Budget
PRJ-016 | Shomolu Staff Clinic | Labour | Masonry gang | 1100000 | 1180000 | 2024-02-01 | Superstructure | 80000 | 7.2727 | Over Budget
PRJ-016 | Shomolu Staff Clinic | Materials | Roofing and ceiling | 1350000 | 1420000 | 2024-03-01 | Finishing | 70000 | 5.1852 | Over Budget
PRJ-017 | Alimosho Model School | Materials | Ceramic floor tiles | 2100000 | 2080000 | 2024-04-01 | Finishing | -20000 | -0.95238 | Under Budget
PRJ-017 | Alimosho Model School | Labour | Tiling and screeding | 1400000 | 1500000 | 2024-05-01 | Finishing | 100000 | 7.1429 | Over Budget
PRJ-017 | Alimosho Model School | Materials | Painting and surface prep | 900000 | 970000 | 2024-06-01 | Finishing | 70000 | 7.7778 | Over Budget

## Dashboard
Lagos Construction Cost Analysis 2024
Total Budget (NGN) | Total Actual (NGN) | Total Variance (NGN) | %Project Over Budget
165080000 | 174460000 | 9380000 | 62.7451